## Consolidated Tasks and Timeline
Workstream | Content Type | Step | Workstream Owner | Current Status | Step Completion Target Date | Notes | 2014-06-30 | 2014-07-07 | 2014-07-14 | 2014-07-21 | 2014-07-28 | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29
Kentico | Pharmaview reports | Qualitative Content Tree | Sam | Prototype complete - awaiting content load | 2014-07-11
Kentico | Pharmaview reports | Entity Provider | Sam | Framework complete | 2014-07-18
Kentico | Pharmaview reports | Report Assembler | Sam | Framework complete | 2014-07-18
Kentico | Pharmaview reports | Frontend Extensions | Sam | In progress | 2014-07-25
Kentico | Pharmaview reports | Content Providers (Tables, Figures, Text) | Sam | In progress | 2014-08-01
Kentico | Pharmaview reports | Report Publisher | Sam | Not Started | 2014-08-01
Kentico | Pharmaview reports | Import/Transformation of Existing Content | Sam | Not Started | 2014-08-31
Kentico | Pharmaview reports | Report Structure Improvements | Sam | Not Started | 2014-09-30
Qualitative Content Migration | Drug Profiles | Rewrite Drug Profiles in Summary Form in Word | Ben | In Progress | 2014-09-20
Qualitative Content Migration | Drug Profiles | Import Existing Drug Profiles into Kentico | Sam | Not Started | 2014-08-31
Qualitative Content Migration | Drug Profiles | Import New Drug Profiles from Word into Kentico | Sam | Not Started | 2014-09-30
Qualitative Content Migration | Company Strategy Content | Company Strategy Content | Ben | Not Started | 2014-10-27
Data Process and Repository | All Data Feeds | Establish process to create regular copy of PVP/BDL database, identify taxonomic links | Ali / Sam / Simon? | Not Started | 8/1/2014? | Sam suggests we set up a regular copy of all PVP tables into new data repository
Data Process and Repository | All Data Feeds | Define PV_BDL_Data_Repository data schema (will feed Kentico tables and charts & Tableau dashboards) | Sam / Simon? | Not Started | 8/1/2014? | Sam and Simon to provide guidance here?
Data Process and Repository | All Data Feeds | Establish PV_BDL_Data_Repository for aggregating data feeds (will feed Kentico tables and charts & Tableau dashboards) | Ali | Not Started | 8/8/2014?
Data Process and Repository | All Data Feeds | Validating Structure and Formatting of Data Files (Sales, Pipeline, Deals, Financials) to Allow Compatibility With Content Providers | Sam / Simon? | Not Started | 8/8/2014?
Data Feeds | PVP Taxonomy Feed | Establishing an extract from PVP that describes entity relationship information | Sam | Not Started | 8/1/2014? | Sam to work with Ben to understand how taxonomy changes as analysts create new classes, DGs, companies etc in PVP
Data Feeds | PVP Superset Data Feed | Establish and Validate Superset Extract from PVP (sales, pipeline, events, etc) | Claude/ Graeme | In progress | 8/1/2014? | Graeme providing feedback
Data Feeds | PV Sales Data | PVP Sales Data Extraction and Data Source File Creation | Claude/ Graeme | In progress | 8/8/2014? | Dedicated sales only feed? Events feed?
Data Feeds | PV Pipeline Data | PVP Pipeline Data Extraction and Data Source File Creation | Andrew | Completed | 2014-07-25 | Pipeline extract sent to Simon & Brigham for reconciliation
Data Feeds | PV + BDL Pipeline Data | Pipeline Taxonomy & Reconciliation Process | Brigham | In progress | 2014-08-08 | BH & SR to present to group after reconciliation. Weekly reconciliation/merge?
Data Feeds | PV + BDL Pipeline Data | Combine PV and BDLive pipeline data into a single source data file + document workflow | Simon | Not Started | 8/15/2014?
Data Feeds | PV Deals Data | Establish Whether BDLive Deals Data is Suitable for use in Reports; additional companies | Ben / Brigham | Not Started | 7/25/2014? | Ben to send deals export from PV to Brigham (BD: completed 16/07/2014); Brigham to work on reconciliation - present back results (week ending 25th)
Data Feeds | PV Deals Data | PVP Deals Data Extraction and Data Source File Creation | Claude/ Graeme | Not Started | 8/15/2014?
Data Feeds | Financials Data | Finalize Agreement with CapIQ | Ben | In progress | 2014-08-01 | Ben to follow up with Rori at CapIQ to finalize - if legal gets involved this could blow up timeline; BD (25/07/14) - received email from Rori confirming that she has secured the required changes as part of the current contract. Ali to work with CapIQ to progress towards completion of this step.
Data Feeds | Financials Data | Map Company IDs to CapIQ Companies | Ben / Mohammed? | Not started | 8/15/2014? | Once finalized CapIQ companies
Data Feeds | Financials Data | Pull Financials Data Feed from CapIQ using API, put in combined repository | Ali | Not Started | 8/15/2014?
Data Feeds | Financials Data | PVP Ethical Drug Sales Data Extraction and Data Source File Creation | Claude/ Graeme | Not Started | 8/15/2014? | Ben to confirm whether ED totals needed
Tableau Dashboards | PV Sales Data | Load current Pharmaview dataset to dashboard (existing extracts) | Brigham | Complete | 2014-07-11
Tableau Dashboards | PV Sales Data | Refine layout of tabs in dashboard | Ben / Brigham / Graeme | In progress? | 2014-07-25 | BD: Need to see dashboard with correct data before starting to work on layout. Awaiting link to this dashboard from BH.
Tableau Dashboards | PV Sales Data | Ensure dashboad is pulling all data correctly | Ben / Graeme | Not Started | 2014-07-25 | BD: Can be done once we receive the link to the updated dashboard
Tableau Dashboards | PV Pipeline Data | Provide Brigham with most recent pipeline dataset | Andrew | Complete | 2014-07-16
Tableau Dashboards | PV + BDL Pipeline Data | Load reconciled PV + BDLive dataset to Pipeline dashboard | Brigham | In progress | 8/15/2014?
Tableau Dashboards | PV + BDL Pipeline Data | Ensure dashboad is pulling all data correctly | Ben / Graeme | Not Started | 8/15/2014?
Tableau Dashboards | PV Deals Data | Load deals data (reconciled?) to deals dashboard | Ben / Brigham / Graeme | Not Started | 2014-08-01
Tableau Dashboards | PV Deals Data | Finalize layout, data download, navigation etc of deals dashboard | Ben / Brigham / Graeme | In progress | ?
Tableau Dashboards | Clinical Trials | Finalize layout, data download, navigation etc of clinical trials dashboard | Brigham | Complete? | ?
Tableau Dashboards | Backend | Deploy usage statistics logging - who accessed which dashboards and when | Brigham / Ali | Not Started | ? | Brigham / Ali to provide date
Gateway Enhancements | Pharmaview reports | Related Content Sidebar within Reports | Andrew | Not started | 2014-08-31
Gateway Enhancements | Tableau dashboards | External Products Rendered within Gateway | Andrew | Not started | 9/30/2014? | Could prove a bit tricky and require additional internal development help (not just PI)
Gateway Enhancements | Pharmaview reports | Product Specific Headers | Andrew | On hold | 10/31/2014?
Gateway Enhancements | Pharmaview reports | Keyword Highlighting and Dynamic Search within Reports | Andrew | On hold | 11/30/2014?
Gateway Enhancements | RSS feeds | News Feeds within Reports | Andrew | On hold | TBD
Gateway Enhancements | RSS feeds | News Feeds for Delivering Real-Time Aggregated Content | Andrew | On hold | TBD
Gateway Enhancements | Pharmaview reports | Search Results at More Granular Level | Andrew | On hold | TBD
Gateway Enhancements | Pharmaview reports | Figure and Table Search Across Reports | Andrew | On hold | TBD
Gateway Enhancements | Pharmaview reports | Contact Report Authors | Andrew | On hold | TBD
Gateway Enhancements | Pharmaview reports | Hyperlinking across PV reports via TOC | Andrew / Sam | On hold | TBD | Sam and Andrew may be able to handle this on Kentico/Gateway side without development
Gateway Enhancements | Pharmaview reports | Full report-type listings on home pages for report types (e.g. home page to list all companies covered all Tas covered all DGs covered etc) | Andrew / Sam | On hold | TBD | Sam and Andrew may be able to handle this on Kentico/Gateway side without development
A&E Development | Tableau Dashboards | A&E authentication for Tableau (short term - shared user and all or nothing access) | Ali | Complete | 2014-06-30
A&E Development | Tableau Dashboards | Provide business rules for Tableau integration | Brigham | In progress | 7/25/2014?
A&E Development | Tableau Dashboards | A&E Authentication for Tableau (entitle each dashboard as separate application within A&E - same as existing HLI or Biopharma dashboards) | Ali | Not Started | ? | AGM: The current logic, which inplies that all users who get Pharmaview also get all the BDLive dasbhoards, should be removed)
A&E Development | Tableau Dashboards | A&E Authentication for Tableau (entitle each dashboard as separate application within A&E - can be applied at user or account level) | Ali | Not Started | ?
New Data Content | Regional Sales Data | Capture Historical Company & Drug Level Regional Sales from 2009-2013 for all PV companies + those with 2013 blockbusters | Ben | In progress | Complete
New Data Content | Regional Sales Data | Standardized company level data | Ben | Not Started | 2014-08-01 | Ben working on company standardizations - expecting to complete by 31/7/14
New Data Content | Regional Sales Data | Drug-level Sales Standardizations | PV Team | Not Started | 2014-10-15 | Ben Duncan: I can do some of this but will need input from the analysts, which may need to wait until after the next forecasting round.
Marketing Collateral | Marketing | Prepare materials to aid sales with both current and prospective clients | Ben | Not Started | 9/1/2014?
Beta Testing / User Feedback | Client feedback | Get feedback from clients on navigation, download, search, enhancements etc | Andrew (platform) / Ben (reports) / Brigham (dashboards)? | Not Started |  | To be provided when we have a beta site ready for testing
Launch | Launch | Target launch date | Ben | Not Started |  | To be provided when project plan finalized and all necessary steps accounted for (currently Q4 has been the goal)
Note on G29: Ben Duncan: Note to Andrew & Ali: The Ethical Drug totals will be extracted from PVP as part of the above sales data extract. These totals are DR calculated, and are not from CapIQ. We have no financials data in the PVP database that we need to extract. In my regional sales data files, I have captured total company sales. The ED totals will be present in the above sales data extract; we can therefore present ED totals as a % of total company sales. Let me know if you need to discuss.